LUMINA LIVING · APPROVED

Project Brief — Sustainable Workspace Campaign

Approved by: Head of Marketing.  Approval date: 12 September 2026.  Version 1.0.

1. Purpose

Lumina Living will launch the Sustainable Workspace campaign to grow corporate demand for our low-carbon workspace range and to establish the brand in the 50–250 staff office segment.

2. Objectives

Generate SGD 940,000 of campaign-attributed revenue in the six months from launch.

Achieve a blended conversion rate of at least 4.0% across Web, Retail and Partner channels.

Hold blended margin at or above 32% for the campaign period.

3. Scope

In scope: the Ergo Desk, Task Chair, Acoustic Pod and Sit-Stand Riser lines across the North, South, East and West regions. Out of scope: export markets and the residential range.

4. Milestones

Creative sign-off — 12 September 2026 — Marketing.

Channel launch — 5 October 2026 — Marketing and Retail.

Post-launch review — 16 November 2026 — Marketing and Finance.

5. Budget

Total approved budget is SGD 185,000, covering creative production, paid media, retail point-of-sale and partner enablement.

6. Risks

Supplier lead time on Acoustic Pods may not support October demand.

Retail staff training is not yet scheduled, which risks inconsistent in-store messaging.

Partner channel reporting lags by up to two weeks, delaying performance visibility.

7. Open Questions

Is additional Acoustic Pod stock committed for the launch window?

Who owns the partner reporting lag, and can it be shortened before launch?

Microsoft Copilot for Content Creation and Task Automation · TGS-2024042588 · Version v1.0 · © 2026 Tertiary Infotech Academy Pte Ltd