LUMINA LIVING · LAB 10 SOURCE

Meeting Notes — Sustainable Workspace Launch Review

Date: 14 September 2026.  Attendees: Priya Raman (Marketing, chair), Daniel Ong (Supply), Sofia Alvarez (Retail), Marcus Lim (Finance), Aisha Rahman (Partner channel).

These notes are unstructured on purpose: decisions, actions and open questions are mixed together, and one item was discussed but never agreed.

Notes

Priya opened by confirming the launch date remains 5 October. Everyone agreed.

Daniel said Acoustic Pod stock lands 19 October, so that line is held back to week three. Agreed.

Sofia said retail training is still not scheduled. Priya agreed to confirm a date by 19 September.

Marcus said the 940k revenue target assumed all four lines from week one, and the phasing now needs re-running. He will produce a revised phasing by 23 September.

There was a discussion about increasing paid media spend by 15k to compensate for the held-back line. Marcus was not comfortable without the revised phasing. No decision was reached.

Aisha raised that partner reporting lags two weeks. She will ask the partner for weekly data and report back by 26 September.

Sofia asked whether the retail point-of-sale material should mention Acoustic Pods at all in week one. This was not resolved.

Priya confirmed the post-launch review stays on 16 November.

Daniel noted that if the 19 October stock date slips, the week-three plan fails. He will flag immediately if the supplier changes the date.

Microsoft Copilot for Content Creation and Task Automation · TGS-2024042588 · Version v1.0 · © 2026 Tertiary Infotech Academy Pte Ltd